## Slide 1
Initiating
Requirements
Design
Development
QA
UAT
Closing
No | Milestone Description | Baseline Target | Actual Target
1. | 3D Anatomy development | 21 Sep 2016 | 5 Aug 2016
2. | Application freezing issue in Firefox | 30 Sep 2016 | 17 Aug 2016
Accomplishments / Progress
Dissectible Anatomy Defect fixed
Release schedule / Next in Queue | Target
Bug Fixing in DA | 7 Oct 2016
Incidents Count |  |  |  | 
Status | Low | Medium | High | Critical
Open |  |  | 30 | 8
In QA |  |  | 7 | 4
Closed |  |  | 29(major) | 5
Test Cases | 
Status | Count
Passed | 
Failed | 
Not Run | 
Tasks Count | 
Status | Count
In Progress | 2
Completed | 4
Not Started | 0
Health Indicators | 
Category | G/Y/R
Scope | Y
Schedule | G
Risks/Issues | G
Risks/Issues/Other Comments
Project Name: | Adam Interactive Anatomy |  | Report Date: |  | 9 Sep 2016
Project Manager: | Ashish Jain | Technical Lead: | Amrita Vishnoi | Completion Dt: | 2 Sep 2016
 | Closed Reference Points