## Slide 1
Initiating
Requirements
Design
Development
QA
UAT
Closing
No | Milestone Description | Baseline Target | Actual Target
1. | Dissectible Anatomy (Extract, Tool bars, Body System Highlight, List Manager, Search, Multi Layer Annotation) | 5 Aug 2016 | 5 Aug 2016
2. | Critical Blacking issue in multiple cases (Highlight, List manager and search, Transpierce box etc.) | 5 Aug 2016 | 17 Aug 2016
3. | Setting Integration- skin tone and modesty | 05 Aug 2016 | 23 Aug 2016
4. | Annotation Toolbar in progress | 05 Aug 2016 | In Progress
Accomplishments / Progress
Dissectible Anatomy Interdependent buttons integration. Defect fixed Optimization for loading DA json. Settings and Annotation tool bar. Lab Exercise in progress Annotation Toolbar in progress
Release schedule / Next in Queue | Target
Dissectible Anatomy | 2 Sep 2016
Bug Fixing in DA | 20 Sep 2016
Incidents Count |  |  |  | 
Status | Low | Medium | High | Critical
Open | 29 |  | 30 | 8
In QA | 6 |  | 7 | 4
Closed | 35 |  | 29(major) | 5
Test Cases | 
Status | Count
Passed | 
Failed | 
Not Run | 
Tasks Count | 
Status | Count
In Progress | 2
Completed | 4
Not Started | 0
Health Indicators | 
Category | G/Y/R
Scope | Y
Schedule | G
Risks/Issues | G
Risks/Issues/Other Comments
Project Name: | Adam Interactive Anatomy |  | Report Date: |  | 9 Sep 2016
Project Manager: | Ashish Jain | Technical Lead: | Amrita Vishnoi | Completion Dt: | 2 Sep 2016
Current Reference Points | Closed Reference Points
Aug 5 2016/Dissectible Anatomy |