## Slide 1
Initiating
Requirements
Design
Development
QA
UAT
Closing
No | Milestone Description | Baseline Target | Actual Target
1 | Login Functionality | 14 Feb 2017 | 22 Feb 2017
2. | AOD module integration | 27 Feb 2017 | 27 Feb 2017
Accomplishments / Progress
Dissectible Anatomy Defect fixed 2. Login page – Completed 3. Dissectible Anatomy – Defect fix in progress 4.Migration from SQL to Mongo DB – in progress
Release schedule / Next in Queue | Target
13 Feb 2017 | 
20 Feb 2017 | 
Next in Que: 3 March 2017 and 20 March 2017 | 
Incidents Count |  |  |  | 
Status | Low | Medium | High | Critical
Open | 5 | 12 | 29 | 5
In QA | 0 | 0 | 0 | 0
Closed | 2 | 7 | 13 | 0
Test Cases | 
Status | Count
Passed | 2
Failed | 1
Not Run | 44
Tasks Count | 
Status | Count
In Progress | 1
Completed | 2
Not Started | 0
Health Indicators | 
Category | G/Y/R
Scope | Y
Schedule | 
Risks/Issues | 
Risks/Issues/Other Comments
Project Name: | AIAHTML5 |  | Report Date: |  | 10 March 17
Project Manager: | Ashish Jain | Technical Lead: | Amrita Vishnoi | Completion Dt: | 28 Feb 2017
Current Reference Points | Closed Reference Points
Product Sprint 33/30-March-17/Bug fixing and New development |