## Slide 1
Initiating
Requirements
Design
Development
QA
UAT
Closing
No | Milestone Description | Baseline Target | Actual Target
1. | Dissectible Anatomy (Extract, Tool bars, Body System Highlight, List Manager, Search, Multi Layer Annotation) | 31 July 2016 | In Progress
2. | Introduced multi threading in angular JS to optimize. | 31 Aug 2016 | In Progress
3. | Transparency issue is fixed Male and Female Lateral Arm. | 31 July 2016 | 31 July 2016
4. | Navigator Man functionality. | 31 July 2016 | 31 July 2016
5. | Annotation Toolbar | 5 Aug 2016 | In Progress
Accomplishments / Progress
Dissectible Anatomy All 10 side tool bar buttons are completed in DA module. Completed the Extract functionality Some Defects fixed. Settings and Annotation tool bar in progress. Optimization are in progress. Interdependent buttons are in progress.
Release schedule / Next in Queue | Target
Dissectible Anatomy | 5 Aug 2016
Optimization of DA | 31 Aug 2016
Incidents Count |  |  |  | 
Status | Low | Medium | High | Critical
Open |  |  |  | 
In QA |  |  |  | 
Closed |  |  |  | 
Test Cases | 
Status | Count
Passed | 
Failed | 
Not Run | 
Tasks Count | 
Status | Count
In Progress | 4
Completed | 8
Not Started | 0
Health Indicators | 
Category | G/Y/R
Scope | Y
Schedule | G
Risks/Issues | G
Risks/Issues/Other Comments
Project Name: | Adam Interactive Anatomy |  | Report Date: |  | 8 Aug 2016
Project Manager: | Ashish Jain | Technical Lead: | Amrita Vishnoi | Completion Dt: | 5 Aug 2016
Current Reference Points | Closed Reference Points
Aug 5 2016/Dissectible Anatomy |