## Slide 1
Initiating
Requirements
Design
Development
QA
UAT
Closing
No | Milestone Description | Baseline Target | Actual Target
1. | Dissectible Anatomy (Toolbars, Highlight Functionality, Term boxes, Transparency box functionality) | 15 July 2016 | In Progress
2. | Clinical Illustrations | 15 July 2016 | 12 July 2016
Accomplishments / Progress
Dissectible Anatomy 5 out 10 side tool bar buttons are completed in DA module. Completed the highlight functionality. All body views integration is completed Transparency in progress for Male/Female Lateral view Bug fixing in progress. Clinical Animations module is in progress
Release schedule / Next in Queue | Target
Dissectible Anatomy | 31 July 2016
Clinical Animations | 31 July 2016
Incidents Count |  |  |  | 
Status | Low | Medium | High | Critical
Open |  |  |  | 
In QA |  |  |  | 
Closed |  |  |  | 
Test Cases | 
Status | Count
Passed | 
Failed | 
Not Run | 
Tasks Count | 
Status | Count
In Progress | 2
Completed | 6
Not Started | 1
Health Indicators | 
Category | G/Y/R
Scope | Y
Schedule | G
Risks/Issues | G
Risks/Issues/Other Comments
1. We have observed that highlight is slow so we need to work on optimization in July (issue)
Project Name: | Adam Interactive Anatomy |  | Report Date: |  | 12 July 2016
Project Manager: | Ashish Jain | Technical Lead: |  | Completion Dt: | 
Current Reference Points | Closed Reference Points
July 15 2016/Dissectible Anatomy | 
July 15/2016/Clinical Illustrations | 
July 15 2016/Clinical Animations |