## Slide 1
Initiating
Requirements
Design
Development
QA
UAT
Closing
No | Milestone Description | Baseline Target | Actual Target
1 | Highlight By Body System | 21 Aug 2017 | 21 Aug 2017
2 | Product Sprint 39/30Aug 2017 | 30 Aug 2017 | 30 Aug 2017
Accomplishments / Progress
Dissectible Anatomy Defect fixed 2. Atlas Anatomy Bug fixing in progress 3.Highlight By Body System integration with product is Completed. 4. Terms and condition , wrong attempt, License subscription is implemented in login
Release schedule / Next in Queue | Target
30 Aug 2017 | 30 Aug 2017
Next in Que: 15 Sep 2017 and 28 Sep 2017 | 
Incidents Count |  |  |  | 
Status | Low | Medium | High | Critical
Open | 0 | 3 | 4 | 0
In QA | 0 | 2 | 3 | 0
Closed | 1 | 9 | 22 | 1
Test Cases | 
Status | Count
Passed | 180
Failed | 29
Not Run | 0
Tasks Count | 
Status | Count
In Progress | 
Completed | 
Not Started | 
Health Indicators | 
Category | G/Y/R
Scope | Y
Schedule | 
Risks/Issues | 
Risks/Issues/Other Comments
Project Name: | AIAHTML5 |  | Report Date: |  | 30 Aug 17
Project Manager: | Pankaj Tiwari | Technical Lead: | Amrita Vishnoi | Completion Dt: | 12 Sep 2017
Current Reference Points | Closed Reference Points
Product Sprint 40/30 Sep 2017 | Product Sprint 39/30Aug 2017