## Slide 1
Initiating
Requirements
Design
Development
QA
UAT
Closing
No | Milestone Description | Baseline Target | Actual Target
1 | ADAM on Demand Integration |  | 
2 | Updated latest External Products |  | 
3 | Help Integration |  | 
4 | Available Support form for admin |  | 
Accomplishments / Progress
DA bug fixing In progress. Help integrated AOD module Integrated.
Release schedule / Next in Queue | Target
02March 2017 | 03 March 2017
17 March 2017 ,29 March 2017 | 30 March 2017
Next in queue- 17- April - 2017 | 
Incidents Count |  |  |  | 
Status | Low | Medium | High | Critical
Open | 7 | 7 | 8 | 0
In QA | 0 | 0 | 0 | 0
Closed | 0 | 6 | 3 | 2
Test Cases | 
Status | Count
Passed | 254
Failed | 35
Not Run | 0
Tasks Count | 
Status | Count
In Progress | 
Completed | 
Not Started | 
Health Indicators | 
Category | G/Y/R
Scope | Y
Schedule | 
Risks/Issues | 
Risks/Issues/Other Comments
Project Name: | AIAHTML5 |  | Report Date: |  | 31 March 17
Project Manager: | Ashish Jain | Technical Lead: | Amrita Vishnoi | Completion Dt: | 5 April 2017
Current Reference Points | Closed Reference Points
Product Sprint 34/17-April-17/Bug fixing and New development |