## Guideline
Parameters	Description	LOW	MEDIUM	HIGH
UI	Anything related to creation or updation of user interface of the project	1. Any work related to modification of style sheet, changing of labels, tool tips or other simple UI elements.	1. UI Adjustment to make the content responsive for multiple device/screen sizes	1. Dynamic creation of any UI Element
			2. UI Manipulation based on business logic	2. Integration with JS Panel

				3.Open Multiple modules together.
		2. Module navigation on external wesite.	4	4. Multiple HTML5 Canvas handling together.
Business Logic	Piece of code/classes/algorithm/business rule those resides on both client side and server side.	Little or no business logics at client side, simple data access from jsons.	1. Included Server side business logics i.e. web API integration, which may involve simple calculation, data manipulation.	1. Algorthim writing based on Complex business Logic. 2. Logic for pixel manupilations. 3. Term calculations based on RGB colors. 4. Calculations involved Cordinate system. 5. Optimization through worker process.
Data Manipulation and Mongo DB	This involves:	1.Modification in existing XML attributes.	1. Utilites preparations for xml to json conversion as per required format in project	1. Database migration from SQL to Mongo DB by using ADO.net , Linq.
	Anything that requires saving or fetching information from database and analyzing data structures or designing data structures	2	2. Import json object into Mongo DB.	2. Conversion of data get in step 1 into desired json object.
				3

Testing	This involves	1. Writing test cases of 1-2 static screens	1. Integration Testing	1. Integration Testing of more than 2 Modules
	1. Writing Test Cases/ Test Script	2. Testing simple static pages	2. Writing Test Cases	2. System Testing
	2. Review and Rework on Test Cases		3. Testing dynamic functionality	3. Writing Test Cases for multiple cases.
	3. Execution of Test Cases			4. Any complex business requirement
	4. System Testing
	5. Integration Testing

R&D	Any research that has to be completed before actually implementing something new

Configuration	This involves configuration done in Database or static file (json) to support working of various process or user interfaces.		1.Import Json object in Mongo DB.

Note
1. No.of Unit - It is the size of the change/request received. Eg.-If there is a UI change of "High Complexity" which involves changing 15 controls then "unit" will be 1 and if requires changing 30 controls then "unit" will be 2.
2. If your project involves special estimation of Testing/BA/Configuration efforts than it can be added as a reference instead of flat calculation at end of the sheet.

## Estimation Template
Project	AIA HTML5	Technology:	.Net
Version :	V1.0.36
Project Release:	Planed Release 29 March 2017
Development Sprint:	Planed Sprint 28 March 2017
Metrics Reference Point:	Product Sprint 33/30-March-17
Created By :	Amrita Vishnoi	Created On:	6-Mar-17
Modified by :		Modified on:
Approved By :	Ashish Jain	Approved On:

Reference Number	Requirement Short Description	Parameter	Complexity	No. of Unit	Estimated Story Points	Expected Pessimistic Estimate in Hours	Expected Most Likely Estimate in Hours	Expected Optimistic Estimate in Hours	Expected Pessimistic Estimate in Workdays	Expected Optimistic Estimate in Workdays	Final Estimation (Hours)
13714	DA > Annotations drawn on transparency box, should be disappear when user close the transparency box.	Business Logic	Medium	1	2	14.29	6.06	3.85			7
13712	DA > Unable to draw transparency box, when annotation toolbar is open and close after paint.	Business Logic	Medium	3	6	42.86	18.18	11.54			21
13092	DA > List Manger > Drop down buttons display out from the border.	Business Logic	Medium	1	2	14.29	6.06	3.85			7
12336	Annotation Toolbar > If Fill option is unchecked and user do the paint. Paint is display on the page.	Business Logic	Medium	3	6	42.86	18.18	11.54			21
		Business Logic	Medium	1	2	14.29	6.06	3.85			7

			Total Story Points		18		Development Total				63
							Testing Total				13
							BA Total				3
							CM Total				3
							Unplanned Total				16
							Project Maangement Total	Project Management total			9

							Total Time Estimation				107

							One Story Point Estimation				6

## Master
	Weightage for	.Net				Technology Master			Parameter Master
Sr. No.	Parameters	Simple	Medium	Complex		Sr. No.	Technology		Sr. No.	Parameters
1	UI	1	2	3		1	.Net		1	UI
2	Database	1	2	3		2	Java		2	Database
3	Configuration	1	2	3		3	Mobile		3	Configuration
4	Business Logic	1	2	3					4	Business Logic
5	R&D	1	2	3					5	R&D
6	Testing	1	2	3		Complexity Master			6	Testing
						Sr. No.	Complexity
	Weightage for	Java				1	Simple
Sr. No.	Parameters	Simple	Medium	Complex		2	Medium
1	UI	1	2	3		3	Complex
2	Database	1	2	3
3	Configuration	1	2	3
4	Business Logic	1	2	3		Productivity Master
5	R&D	1	2	3		Sr. No.	Productivity
6	Testing	1	2	3		UCL	0.52
						LCL	0.14
	Weightage for	Mobile				Mean	0.33
Sr. No.	Parameters	Simple	Medium	Complex
1	UI	1	2	3
2	Database	1	2	3
3	Configuration	1	2	3
4	Business Logic	1	2	3
5	R&D	1	2	3
6	Testing	1	2	3